## Questionnaire
# | Questions | Mapping | Evidence | Remark
1 | Show me the organization chart. | GP2.1.1
2 | Show the Project Planning in PMP. | GP 2.1.1
3 | What is the scope of the Project, show me the Project Block diagram | GP 2.1.1
4 | What is been expected for project? | GP 2.1.1
5 | Have you planned any reviews for work products? | GP 2.1.2
6 | Have you defined process activities & tasks? | GP 2.1.2
7 | Is every resource logging their efforts in JIRA? | GP 2.1.3
8 | Do you have the Change Control Board? Do you inform customer if any changes occurred? What is the procedure when any change is occurred?? | GP 2.1.4
| Have you taken appropriate actions when the planned objectives are not achieved? | GP 2.1.4
9 | Show me the roles & responsibilities of every team memebers. | GP 2.1.5
10 | Show me the skilll matrix & Training Plan | GP 2.1.5
11 | Do you have any verification review or confirmation review? | GP 2.1.5
12 | Are you maintaining Validation report? | GP 2.1.5
13 | Do you have specific task for every resources & where it is been documented? | GP 2.1.6
14 | Show me the monthly leave plan for each resources. | GP 2.1.6
15 | Show me the Project Status Report. | GP 2.1.7
16 | Are you maintaining MoM when there is some imp discussion with customer? | GP 2.1.7
17 | Show me the evidence for weekly & monthly meeting | GP 2.1.7
18 | What is the flow of work products? | GP 2.2.1
19 | Are you maintaining review record & have you closed all the review findings? Have you done the re-work? | GP 2.2.1, GP 2.2.4
20 | Have you done check in/check out for documents? | GP 2.2.1
21 | Are you maintaining verification criteria? | GP 2.2.1
22 | Is version control in practice for updated documents? | GP 2.2.2
23 | Show me the Project Gantt chart. | GP 2.2.2
24 | Do you properly accessed the control of work products? Ex: If you are working on Polarian tool then its access should be given to the BR01 team members only. | GP 2.2.2
25 | Show me the Configuration Management Plan. | GP 2.2.3
26 | Did you established the change control for work products? | GP 2.2.3