## Base Practices_v3.1 (hidden)
MANAGEMENT PROCESS GROUP |  | Previous Rating | [6 empty] | Current Evaluation | [5 empty] | Evidence | Remark | Target Date
MAN.3 | PROJECT MANAGEMENT | In Scope? | PA 1.1 | PA 2.1 | PA 2.2 | PA 3.1 | PA 3.2 | CL | PA 1.1 | PA 2.1 | PA 2.2 | PA 3.1 | PA 3.2 | CL
BP1 | Define the scope of work. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP2 | Define project life cycle. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP3 | Evaluate feasibility of the project. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP4 | Define, monitor and adjust project activities. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP5 | Define, monitor and adjust project estimates and resources. | No | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP6 | Ensure required skills, knowledge, and experience. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP7 | Identify, monitor and adjust project interfaces and agreed commitments. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP8 | Define, monitor and adjust project schedule. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP9 | Ensure consistency. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP10 | Review and report progress of the project. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
Note on C3: Identify the project's goals, motivation and boundaries.
Note on C4: Define the life cycle for the project, which is appropriate to the scope, context, magnitude and complexity of the project.
Note on C5: Evaluate the feasibility of achieving the goals of the project in terms of technical feasibility within constraints with respect to time, project estimates, and available resources.
Note on C6: Define, monitor and adjust project activities and their dependencies according to defined project life cycle and estimations. Adjust activities and their dependencies as required.
Note on C7: Define, monitor and adjust project estimates of effort and resources based on project's goals, project risks, motivation and boundaries.
Note on C8: Identify the required skills, knowledge, and experience for the project in line with the estimates and make sure the selected individuals and teams either have or acquire these in time.
Note on C9: Identify and agree interfaces of the project with other (sub-) projects, organizational units and other affected stakeholders and monitor agreed commitments.
Note on C10: Allocate resources to activities, and schedule each activity of the whole project. The schedule has to be kept continuously updated during lifetime of the project.
Note on C11: Ensure that estimates, skills, activities, schedules, plans, interfaces, and commitments for the project are consistent across affected parties.
Note on C12: Regularly review and report the status of the project and the fulfillment of activities against estimated effort and duration to all affected parties. Prevent recurrence of problems identified.

## Work Products_v3.2 (hidden)
MAN.3 | Project Management
08-12 | Project plan
13-04 | Communication record
13-16 | Change request
13-19 | Review record
14-02 | Corrective action register
14-06 | Schedule
14-09 | Work breakdown structure
14-50 | Stakeholder groups list
15-06 | Project status report

## Base Practices_v4.0
MANAGEMENT PROCESS GROUP |  | Previous Rating | [6 empty] | Current Evaluation | [5 empty] | Evidence | Remark | Target Date
MAN.3 | PROJECT MANAGEMENT | In Scope? | PA 1.1 | PA 2.1 | PA 2.2 | PA 3.1 | PA 3.2 | CL | PA 1.1 | PA 2.1 | PA 2.2 | PA 3.1 | PA 3.2 | CL
BP1 | Define the scope of work. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP2 | Define project life cycle. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP3 | Evaluate feasibility of the project. |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP4 | Define and monitor work packages |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP5 | Define and monitor project estimates and resources |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP6 | Define and monitor required skills, knowledge, and experience |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP7 | Define and monitor project interfaces and agreed commitments |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP8 | Define and monitor project schedule |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP9 | Ensure consistency |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
BP10 | Review and report progress of the project |  | - | - | - | - | - | 0 | - | - | - | - | - | 0
Where the customer approval mails has been stored?
Note on B3: Identify the project's goals, motivation and boundaries.
Note on B4: Define the life cycle for the project, which is appropriate to the scope, context, magnitude and complexity of the project.
Note on B5: Evaluate the feasibility of achieving the goals of the project in terms of technical feasibility within constraints with respect to time, project estimates, and available resources.
Note on B6: Define and monitor work packages and their dependencies according to defined project life cycle and estimations.
Note on B7: Define and monitor project estimates of effort and resources based on project's goals, project risks, motivation and boundaries. Note 5: Examples of necessary resources are budget, people, product samples, or infrastructure Note 6: Project risks (using MAN.5) may be considered. Note 7: Estimations and resources may include engineering, management and supporting processes
Note on B8: Identify and monitor the required skills, knowledge, and experience for the project in line with the estimates and work packages. Note 8: Training, mentoring or coaching of individuals may be applied to resolve deviations from required skills and knowledge.
Note on B9: Identify and agree interfaces of the project with affected stakeholders and monitor agreed commitments. Define an escalation mechanism for commitments that are not fulfilled. Note 9: Affected stakeholders may include other projects, organizational units, sub-contractors, and service providers.
Note on B10: Allocate resources to work packages and schedule each activity of the project. Monitor the performance of activities against schedule.
Note on B11: Regularly adjust estimates, resources, skills, work packages and their dependencies, schedules, plans, interfaces, and commitments for the project to ensure consistency with the scope of work. Note 10: This may include the consideration of critical dependencies, that are an input for risk management.
Note on B12: Regularly review and report the status of the project and the fulfillment of work packages against estimated effort and duration to all affected parties. Prevent recurrence of identified problems. Note 11: Project reviews may be executed at regular intervals by the management. Project reviews may contribute to identify best practices and lessons learned. Note 12: Refer to SUP.9 for resolution of problems

## Information Item_v4.0
MAN.3 | Project Management
08-53 | Scope of work
08-54 | Feasibility analysis
14-10 | Work package
13-52 | Communication evidence
13-16 | Change request
13-51 | Consistency evidence
14-02 | Corrective action
18-52 | Escalation path
08-56 | Schedule
14-50 | Stakeholder groups list
15-06 | Project status

## Rating Description
PROCESS ATTRIBUTES (PA)
Process attributes are features of a process that can be evaluated on a scale of achievement, providing a measure of the capability of the process. They are applicable to all processes.
According to ISO/IEC 33020 there are six capability levels, incorporating nine process attributes:
RATING SCALE
Within this process measurement framework, a process attribute is a measureable property of process capability. A process attribute rating is a judgement of the degree of achievement of the process attribute for the assessed process.
The rating scale is defined by ISO/IEC 33020 as shown in table below:
The ordinal scale defined above shall be understood in terms of percentage achievement of a process attribute.
The corresponding percentages shall be:

## Drop down list (hidden)
-
N
P
L
F
Yes
No