## Document History
Date | Author | Remark
2023-09-15 | Nishant Kumar | LL_01 and LL_02 updated

## Lessons Learned
Lessons Learned
Project name: |  | BR |  |  | Project number: | 01
Project manager: |  | Shubhada Bhagatkar |  |  | Project sponsor: | Nishant Kumar / Chandram Yegapagol
ID | Date raised | Incident (what happened) | Project Phase | Lesson category | Lesson Learnt | Recommendations | Preventive Action(s) | Owner | Status | Closed Date
BR01_LL_01 | 2023-09-07 | Information received from ASW Lead for Development plan Estimation | Project Concept | Negative | Cross Functional Team shall always receive information from Single Point Of Contact to avoid rework or miscommunicaiton. | Get First hand infromation from SPOC | Communicate to all BR01 Team Leads and SPOC in Weekly meeting. | Team Leads | Closed | 2023-09-07
BR01_LL_02 | 2023-09-07 | BR01 Master plan dates not matching as per VRT Master Plan | Project Concept | Negative | Any Communication impacting QCD shall be communicated over email and informed to all impacted stakeholders. | Communication over email clearly mentioning impact on Quality, Cost and Deliver with Rational shall be documented. | Share email Template to BR01 Team Leads and sPOC in Weekly meeting. | Nishant Kumar | Closed | 2023-09-29
BR01_LL_03 | 15/09/2023 | Issues faced with customer while translating documents from Chines to English using Google or free online translation tool in a another project | Project Concept | Negative | To avoid data privacy breach of any kind, we must have a formal agreement from customer where translations are required. | To install an offline, secure software tool for translations | Communicate to all team members sensitizing the lesson learnt | Shubhada Bhagatkar | Closed | 2023-09-29
BR01_LL_04 | 2023-03-11 | The risk assessed for project were overdrametized leading to think that project was risky | Project Concept | Negative | The risks were made to look so severe that customer thought the project should not be implemented | To have realistic apporch while mentioning risks. | Making all aware on the approach one nees to have while assessing the risks | Shubhada Bhagatkar | Closed

## Template History
# | Date | Reviewer | Remark

## Drop down (hidden)
Staus | Lesson Category
Open | Positive
In Progress | Negative
Closed