## F6_Release
Challenge Faced | Description | Impact | Resolution / Mitigation | Lessons Learned
Automation Scripts were not working | 1. initially we have tried to run automation scripts but we faced problem to set up the environment 2. Later we decided to take the previous sanity test tool and test integration software 3. report of automation test was not matured, messages are failed | consumed time for integration test | Rework on automation tests | If we are testing using automation scripts, then we have to be prepared and ready with scripts before integration done.
Routed messages are failed in Automation scripts | 1. we found difficulty to find the routed message in the report generated by automation script 2. it was time consuming to find the routed messages 3. we have performed manual testing for few routed messages and concluded | time consuming and manual efforts are more | Automation for routed messages | Prepare Document of routed messages so we can find easily
Manully Differentiated messages not implemented, not tested, failed,passed | 1. After sanity test from tool, we had to manully differentiate and get the count of passed, failed and not implemented tests 2. we had to compare TC_Magna and check which are not implemented | Manual effort in this type of comparision leads to mismatch data | work on scripts so we can get the count in report | Manual efforts leads to mismatch data, Try to automate everything for next release
Problem in Uploading binaries to sharepoint | 1. After sanity check we have to upload binaries to sharepoint including all tested resports 2. Testing team have to take binaries from sharepoint 3. Testing team has reported that the binaries are not working | Time consuming for Testing team | re-uploaded the binaries to sharepoint | Sometime Uploading to sharepoint will not happen properly, we have to verify binaries after uploading to sharepoint
Init Value Missmatch | 1. init value is initailly set by davinci tool in developer. 2. Matlab is changinf the init value though some ways 3. when we again try to integrate ARXML generated from matlab to developer the we face init missmatch issue | Developer Team has to set all Init values back to default Values | Matlab team Has to check from Matlab side | creates Delay and Imperfections
Code mapping | 1. New code mapping will be added by matlab team 2. Intead Matlab should use the old code mapping which is already available in memory section | Multiple Code Mapping should be done in davinci developer which creates confusions | Instead of creating new mwmory sections, Matlab team has to use the already available memory sections | Time consuming and Imperfections
MATLAB cannot import code mapping set from davinci arxml export | 1. After exporting ARXML file from Davinci Developer 2. MATLAB cannot import and shows error like "cannot find the referenece for code block in memory sections" 3. if we manually remove this code block the the error resolves | everytime davinci team has to r emove code section manually | MATLAB team has to find solution and have to find the reeference for the code block in memory section | Time consuming and Imperfections